MINUTES OF MEETING

EC P2 Sprint 0 – AEM Assets, DAM Strategy & Migration Approach

| Date | June 17, 2026 |
| --- | --- |
| Time | As per recording (approx. 9:00 AM – 11:30 AM) |
| Meeting Type | Sprint 0 Refinement – Asset Details, Council Requirements, Migration Approach, DAM Strategy |
| Facilitated by | Adobe Team (Tushar / Priya / Suman) |
| Attendees – Adobe | Tushar, Priya, Suman, Shikha (and other Adobe team members) |
| Attendees – GSUSA | Michelle, Peter, Daria, Tracy, Harsha, Derek (Kelly & Caitlyn on PTO; Marianne & Haley Workman not present) |
| Recording | Meeting was recorded |
| Reference Document | DAM Strategy Workbook (filled by GSUSA team) |

# 1.  AGENDA

- Review DAM Strategy Workbook (Folder Structure, Taxonomy, Metadata Schema, Permissions)

- Clarify asset consumption channels

- Discuss vendor & council upload access and permissions

- Review migration approach from Webdam / SharePoint / NetSuite to AEM DAM

- Language / multi-locale considerations

- Next steps and open items

# 2.  KEY DISCUSSION SUMMARY

2.1  Asset Consumption Channels

The Adobe team sought clarity on where AEM DAM assets would be consumed beyond the main website being developed. GSUSA confirmed the following consumption channels:

- girlscoutshop.com (primary)

- girlscouts.org and 110 council websites

- Email marketing (via Dispatch tool used by GSUSA graphic designers)

- Social media (assets downloaded and posted by team)

- Leader Tools application (separate AEM instance – future convergence planned)

- Councils’ own marketing materials, stores, and websites

Direct system-to-system integrations (e.g. AEM → social media or email tool) are out of scope for this engagement. Assets will either be published via URL or downloaded and used manually.

2.2  Folder Structure Decisions

Several folder structure clarifications were made:

- The comment ‘unauthorable website assets’ on certain folders (e.g. curriculum, photo shoots) is legacy noise and can be deleted.

- All 110 councils will have a similar Level 3 sub-folder structure beneath their respective council folders.

- Council ‘100’ (Girl Scout Central) is owned by GSUSA and should be treated as a GSUSA folder, not a council. Row 126 to be deleted from the workbook.

- Council 800 is to be treated like a regular council.

- Folder names cannot contain forward slashes (/). These will be replaced with hyphens (e.g. ‘waist/tunic’ → ‘waist-tunic’).

- AEM DAM best practice: Keep fewer than 1,000 assets per folder to avoid performance degradation. Sub-folders can be created if volumes exceed this threshold.

- No workflow stages within folders (assets do not ‘move’ from brand → merchandise etc.). Assets are discrete per folder; archived assets move to the Archive folder manually.

2.3  Taxonomy & Tags

The team reviewed the taxonomy structure in the DAM Strategy Workbook:

- Duplicate tags for ‘Volunteer Appreciation Campaign’ (rows 128–130) were reviewed. Best practice: use a parent tag (general campaign) and apply a year-specific tag alongside it (e.g. ‘Volunteer Appreciation Campaign’ + ‘2026’) so both broad and year-specific filtering is possible.

- Historical taxonomy (1900–2000) is intentionally manually curated – it is NOT an automatic date-based tag. Assets are tagged as ‘historical’ based on iconic significance. The gap from 2000–2024 is intentional for now; new historical buckets can be added in the future as needed.

- Adobe team to review and suggest optimizations to the taxonomy structure, to be discussed at Monday’s follow-up meeting.

2.4  Metadata Schema

Several metadata schema fields (custom tab) were identified as having missing dropdown values (e.g. license type, product data role). Ownership of these fields was unclear during the meeting:

- Adobe team believes certain custom fields were created by the GSUSA team; GSUSA is uncertain.

- It was agreed that Adobe and GSUSA will each review the out-of-box and custom metadata fields independently before Monday’s call.

- Metadata schema approach: Start with one default schema. A lighter schema variant may be created for product/commerce-specific assets that require SKU and commerce-related fields. Final recommendation: one default + one SKU/product-specific schema to start.

- Future metadata schemas (e.g. council-specific or leaders tool-specific) can be added as requirements evolve.

2.5  Permissions & Access Control

Detailed permissions discussions covered GSUSA internal users, councils, and vendors:

GSUSA Internal Users

- GSUSA Content Creators: Full superset access to all DAM folders.

- GSUSA Content Managers: Full access to the Marketing folder; view-only access to all other folders; some folders may be restricted (no access) – to be finalized.

- Tag Management: Content Managers can apply tags to assets. Creating new tags is restricted to a very limited set of admins (e.g. Daria, Caitlyn). This distinction is confirmed.

- Expected GSUSA users with full upload/edit access: ~20 internal users (to be confirmed against existing license terms). Total licensed users discussed: ~15 (to be validated with licensing team).

Council Access

- Authentication: Okta (councils may have their own email domains, not girlscouts.org).

- Each council has full read/write/edit/delete permissions within their own council folder only.

- All councils can view GSUSA-shared folders (global assets, products, marketing, etc.).

- Councils cannot view other councils’ folders.

- Girl Scout Central (council 100) is a GSUSA-owned folder; all councils will have access to it (treated as shared GSUSA resource).

- Certain GSUSA folders will be restricted from council view – specific folders to be identified and labelled (not yet done).

- Number of council users per council: At least 1, likely 2–3 per council (to be confirmed from previous documentation).

Vendor / Agency Partner Access

- Authentication: Okta (separate domain from GSUSA).

- Number of vendors with direct AEM access: 2–3 trusted agency/creative partners.

- Each vendor will have their own dedicated folder (under a Vendor folder, similar to council folder structure).

- Vendor access level: Upload + read within their own folder only. No access to other areas of DAM.

- Asset review process: Daria (GSUSA) will review assets offline before vendors upload only approved assets to AEM. No AEM-native approval workflow for vendor uploads.

- For council-uploaded product images intended for girlscoutshop.com: approval occurs at the Commerce/Adobe publishing layer, NOT within AEM DAM.

2.6  Migration Approach

Current asset sources confirmed:

- Webdam (primary source – individual product images)

- SharePoint (lifestyle photography)

- NetSuite (mentioned in Phase 1 recap as a source)

Key migration decisions and discussions:

- All assets to be consolidated into a single staging location before migration to AEM DAM.

- Assets must be arranged in the staging location in the SAME folder hierarchy as planned for AEM DAM.

- Asset metadata must be prepared in Excel format, reviewed, mapped to the AEM schema, and provided alongside the assets.

- Duplicate/redundant assets must be cleaned up before the final migration dump is provided.

- Recommended staging location options: AWS S3, Microsoft Azure Blob, Google Cloud Storage, Dropbox, or OneDrive. Team consensus leans toward OneDrive (SharePoint), to be confirmed.

- Immediate action: GSUSA to confirm staging location this week, then place a few sample assets (across a couple of representative folders) in OneDrive by Wednesday, June 24 to enable Adobe to run a POC/Spike in Sprint 1.

- Full migration planning and timelines to be discussed in a dedicated data migration meeting.

2.7  Language / Multi-Locale

English is the supported language for initial launch. Spanish is a potential future requirement (not immediate – estimated 2–3 years away).

- Adobe recommendation: If Spanish assets will eventually be needed at scale (same volume as English assets), creating a separate language node/folder structure is the best practice for manageability.

- For Day Zero: No action needed. The solution design document will include a note on the recommended folder structure for future Spanish support as a scalability consideration.

# 3.  ACTION ITEMS

Legend:

■ Adobe  ■ GSUSA  ■ Both   |   Priority: H = High  M = Medium  L = Low

| # | Action Item | Owner | Due Date | Priority |
| --- | --- | --- | --- | --- |
| GSUSA Team Action Items |  |  |  |  |
| 1 | Confirm the staging location for migration assets (OneDrive/AWS S3/Azure etc.) and communicate to Adobe team this week. | GSUSA (Michelle / Peter) | Jun 20, 2026 | High |
| 2 | Set up a sample folder structure in the confirmed staging location (e.g. OneDrive) and upload a few sample assets (from both Webdam and SharePoint sources) across 2-3 representative folders to enable Adobe POC/Spike. | GSUSA (Daria / Tracy) | Jun 24, 2026 | High |
| 3 | Identify and confirm which GSUSA folders should be restricted from council view access (i.e. folders that councils should NOT be able to see). Update the DAM Strategy Workbook accordingly. | GSUSA (Michelle / Peter) | Jun 23, 2026 | High |
| 4 | Review all out-of-box and custom metadata fields in the Metadata Schema (custom tab). Confirm which fields are needed, identify any missing values/dropdowns (e.g. license type, product data role), and bring findings to Monday’s meeting. | GSUSA (Daria / Caitlyn) | Jun 23, 2026 | High |
| 5 | Confirm the number of council users per council (per role) with reference to prior documentation from previous sessions. Tracy to find and share this data. | GSUSA (Tracy) | Jun 20, 2026 | Medium |
| 6 | Validate current AEM Assets license: confirm total licensed user count and how council users + vendors will be accommodated. Check with licensing team / account team. | GSUSA (Michelle / Peter) | Jun 20, 2026 | High |
| 7 | Ensure the following stakeholders are invited to Monday’s follow-up meeting (Jun 23): Rich, Marianne, Haley Workman, Caitlyn, Kelly (if available). | GSUSA (Michelle) | Jun 20, 2026 | High |
| 8 | Delete Row 126 (council 100 / Girl Scout Central council listing) from the DAM Strategy Workbook folder structure tab. Update council 100 to be clearly labeled as GSUSA-owned shared folder. | GSUSA (Michelle / DAM workbook owner) | Jun 23, 2026 | Medium |
| 9 | Review and correct the folder structure for councils in the DAM Strategy Workbook – remove ‘curriculum’ from council sub-folders if it was incorrectly added. | GSUSA (Michelle / Marianne) | Jun 23, 2026 | Medium |
| 10 | Clarify and document asset creation tool(s) currently in use (Adobe suite tools, external agencies, etc.) so Adobe can assess potential native integrations. | GSUSA (Daria / Michelle) | Jun 23, 2026 | Low |
| 11 | Prepare and share the custom domain / lower environment URLs (dev, QA, stage) for girlscoutshop.com with Adobe team – coordinate with Kelly upon return from PTO. | GSUSA (Harsha / Kelly) | Jun 25, 2026 | Medium |
| Adobe Team Action Items |  |  |  |  |
| 12 | Review the out-of-box AEM Assets metadata fields and cross-reference with the custom fields in the GSUSA DAM Strategy Workbook. Identify gaps, ownership, and recommendations. Share findings with GSUSA before Monday’s meeting. | Adobe (Tushar / Suman) | Jun 23, 2026 | High |
| 13 | Propose optimized taxonomy structure for tags – specifically address duplicate volunteer appreciation campaign tags and recommend a parent + year-tag approach. Present during Monday’s meeting. | Adobe (Suman / Priya) | Jun 23, 2026 | High |
| 14 | Confirm technical feasibility and approach for vendor upload-only folder access in AEM (i.e. vendors having upload + read access restricted to their own folder only). Document approach. | Adobe (Tushar) | Jun 23, 2026 | High |
| 15 | Once GSUSA confirms staging location and provides sample assets, execute migration POC/Spike in Sprint 1: test connectivity between staging location (OneDrive) and AEM DAM, validate folder hierarchy mapping, and report findings. | Adobe (Shikha / Tushar) | Sprint 1 | High |
| 16 | Document recommended folder structure design for future Spanish language support (as a scalability note) in the Solution Design Document. No implementation required for Day Zero. | Adobe (Priya / Tushar) | Jun 27, 2026 | Low |
| 17 | Create and share a document / diagram showing the publish approval workflow (swim lane / process flow) for council-uploaded product assets going to girlscoutshop.com, to help GSUSA understand the approval flow at the Commerce/publishing layer. | Adobe | Jun 27, 2026 | Medium |
| 18 | Update the Q&A tracker with the clarified question on custom domains for lower environments (dev/QA/stage) and ensure it is addressed with Harsha and Kelly separately outside this DAM meeting. | Adobe (Priya / Shikha) | Jun 20, 2026 | Medium |
| Joint Action Items (Adobe + GSUSA) |  |  |  |  |
| 19 | Monday follow-up meeting (Jun 23): Reconvene with broader stakeholders (Rich, Marianne, Haley Workman, Caitlyn, Kelly) to finalize open DAM strategy items – folder structure corrections, metadata schema, taxonomy, and migration staging confirmation. | Both | Jun 23, 2026 | High |
| 20 | Schedule dedicated Data Migration meeting to detail the full migration plan: source systems (Webdam, SharePoint, NetSuite), staging location setup, metadata mapping in Excel, asset hierarchy recreation, and timelines for bulk migration. | Both | Jun 27, 2026 | High |
| 21 | Finalize permissions matrix: document all user types (GSUSA staff, councils, vendors), their folder access levels (full / view / none), and which folders are restricted from each user type. Include in Solution Design Document. | Both | Jun 27, 2026 | High |

# 4.  NEXT STEPS & TIMELINE

| Timeline | Next Step | Responsible Party |
| --- | --- | --- |
| By Jun 20 (Fri) | - Confirm migration staging location (OneDrive or alternate) - Validate AEM license user counts with licensing team - Share council user count data (Tracy) - Invite all required stakeholders to Monday’s meeting - Update Q&A tracker with lower environment domains question | GSUSA (Michelle, Peter, Tracy) ¦ Adobe (Priya) |
| By Jun 23 (Mon) | - Follow-up meeting with broader GSUSA stakeholders (Rich, Marianne, Haley, Caitlyn, Kelly) - GSUSA shares metadata schema review findings - Adobe shares taxonomy optimization recommendations - Finalize folder structure corrections in DAM Workbook - Identify restricted folders for councils | Both teams |
| By Jun 24 (Tue) | - GSUSA uploads sample assets to staging location (OneDrive) for Adobe POC - Assets should reflect 2 types: product images (from Webdam) and lifestyle photography (from SharePoint), placed in 2–3 representative folders | GSUSA (Daria / Tracy) |
| Sprint 1 (from Jun 24) | - Adobe runs migration POC/Spike: test OneDrive → AEM DAM connectivity and folder hierarchy mapping - Adobe documents vendor upload-only access approach - Schedule dedicated Data Migration meeting for full planning - Finalize Permissions Matrix in Solution Design Document | Adobe (Shikha, Tushar, Priya) |
| By Jun 27 (Fri) | - Adobe shares publish approval workflow diagram (commerce layer) - Adobe documents Spanish language folder structure recommendation in Solution Design Document - Dedicated Data Migration meeting held | Both teams |

# 5.  DEPENDENCIES & RISKS

| # | Dependency / Risk | Impact if Unresolved | Owner | Status |
| --- | --- | --- | --- | --- |
| D1 | GSUSA must confirm staging location (OneDrive / AWS) before Daria can upload sample assets and before Adobe can plan the POC. | Delays Sprint 1 migration POC and blocks migration timeline. | GSUSA (Michelle / Peter) | Open – Critical |
| D2 | Key GSUSA stakeholders (Marianne, Haley Workman, Caitlyn, Kelly, Rich) were absent from this meeting. Many workbook decisions remain unconfirmed without their input. | Risk of rework on folder structure, metadata schema, and permission design if stakeholders have conflicting requirements. | GSUSA (Michelle) | Open – High |
| D3 | AEM license user count needs validation. Total licensed users (~15) may not accommodate all GSUSA staff + 110 councils (1–3 users each) + 2–3 vendors. | May require license renegotiation or architecture change (e.g. Content Hub for external users). | GSUSA (Michelle / Peter) | Open – Medium |
| D4 | Metadata schema custom fields have unclear ownership (some fields may have been created by Adobe in Phase 1 and not documented). Missing dropdown values block schema finalization. | AEM DAM metadata schema cannot be finalized, delaying configuration and migration metadata mapping. | Both (Adobe + GSUSA) | In Progress |
| D5 | Council product assets (for girlscoutshop.com) have a separate approval workflow at the publishing/Adobe Commerce layer. This workflow diagram has not yet been shared with the GSUSA team in a clear format. | GSUSA team may not correctly understand which approvals happen in AEM vs. Commerce, leading to misaligned process expectations. | Adobe | Open – Medium |
| D6 | Bulk asset migration from Webdam requires downloading/exporting from Webdam and re-uploading to the staging location. This is a significant GSUSA effort and the process/timeline is not yet defined. | Migration go-live could be delayed if the GSUSA content team is not resourced or prepared for the Webdam export effort. | GSUSA (Daria / Michelle) | Open – High |

# 6.  OPEN ITEMS / PARKING LOT

The following items were raised during the meeting but require further offline discussion or a separate forum:

- Custom domains for lower environments (dev, QA, stage) for girlscoutshop.com – to be discussed with Harsha and Kelly separately. Question to be moved to the Q&A tracker.

- Whether vendor image upload requires a separate AEM workflow or can leverage the existing review-offline-then-upload approach – confirmed the latter is preferred by Daria.

- Exact count of council users per role – referenced in prior documentation; Tracy to locate and confirm.

- Leader Tools AEM instance convergence with main AEM – noted as a future consideration by Michelle; not in scope for current engagement but folder structure has been designed to accommodate it.

- Whether any Adobe product suite tools (e.g. Adobe Express, Firefly) are used for asset creation – if yes, native integration options can be explored in a future sprint.

# 7.  DECISIONS MADE IN THIS MEETING

| # | Decision | Agreed By |
| --- | --- | --- |
| 1 | Forward slashes (/) in folder names will be replaced with hyphens (-). | Both |
| 2 | Council 100 (Girl Scout Central) is a GSUSA-owned folder, not a council. Row 126 to be deleted from DAM workbook. | Both |
| 3 | No AEM-native workflow for vendor asset uploads. Daria to review assets offline and only approved ones will be uploaded by vendors. | GSUSA |
| 4 | 2–3 trusted vendors will be given direct AEM access to their own dedicated upload folders only. | GSUSA (Michelle / Peter) |
| 5 | Authentication for both councils and vendors: Okta (with their own domain email addresses). | Both |
| 6 | Tag management (creation of new tags): restricted to 1–2 admin users only (e.g. Daria, Caitlyn). Content managers can apply but not create tags. | Both |
| 7 | One default metadata schema + one lighter SKU/product-specific schema to be created initially. | Both |
| 8 | Spanish language support: no folder structure changes for Day Zero. Recommendation for future scalability to be documented in the Solution Design Document. | Both |
| 9 | Preferred staging location for migration: OneDrive (to be confirmed by GSUSA this week). | Tentative – GSUSA to confirm |
| 10 | Assets that are not ‘historical’ from 2000–2024 will not be tagged. Historical tags are manually curated, not date-based. | Both |

Document prepared by: Adobe Delivery Team  |  Date: June 17, 2026  |  Status: Draft – Pending GSUSA Review