AEM Asset Migration

S3 Bucket to AEM as a Cloud Service
Step-by-Step Migration Process

Includes: Folder Restructuring, Metadata Mapping & Migration Execution

Date: June 2026
Status: Process Guide
Version: 1.0

# Table of Contents

Phase 1: Discovery & Assessment

Phase 2: Target DAM Structure Design

Phase 3: Folder Mapping Rules Definition

Phase 4: Metadata Mapping & Transformation

Phase 5: Migration Tooling & Infrastructure Setup

Phase 6: Pre-Migration Validation & Dry Run

Phase 7: Migration Execution

Phase 8: Post-Migration Validation & QA

Phase 9: Cutover & Go-Live

Appendix A: AEMaaCS Bulk Import Configuration

Appendix B: Metadata Schema Reference

Appendix C: Troubleshooting Guide

# Migration Overview

This document provides a detailed step-by-step process for migrating digital assets from an AWS S3 bucket to AEM as a Cloud Service (AEMaaCS) DAM. The migration includes folder restructuring (rule-based path transformation) and metadata mapping from an external database/CSV source.

## Migration Architecture

| Component | Details |
| --- | --- |
| Source | AWS S3 Bucket (all asset types: images, documents, videos, 3D assets) |
| Target | AEM as a Cloud Service — Assets (DAM) |
| Folder Strategy | Rule-based transformation (rename, merge, flatten, remap paths) |
| Metadata Source | External database/CSV linked by filename or asset ID |
| Migration Tool | AEMaaCS Bulk Import (native S3 connector) + custom scripts for transformation |

## High-Level Migration Flow

S3 Bucket → Folder Transformation (Staging) → Metadata Enrichment → AEMaaCS Bulk Import → Post-Processing → Validation → Go-Live

## Key Constraints & Considerations (AEMaaCS)

| Constraint | Limit / Detail |
| --- | --- |
| Max file size | 50 GB per asset (video); practical limit ~15 GB for processing |
| Max path length | 350 characters (full /content/dam/... path) |
| Max folder depth | 15 levels recommended; deeper paths may cause issues |
| Supported renditions | Original only on import; renditions auto-generated by Asset Compute |
| Concurrent uploads | Bulk Import supports parallel ingestion; rate limits apply |
| Metadata import | Via .csv sidecar files co-located with assets OR post-import API calls |
| Asset naming | No special characters: avoid #, %, {, }, \, <, >, *, ?, /, $, !, @ |
| Duplicate handling | Configurable: skip, overwrite, or version |

# Phase 1: Discovery & Assessment

Objective: Understand the source S3 bucket structure, volume, asset types, and metadata landscape before planning the migration.

## Step 1.1: S3 Bucket Inventory

Goal: Generate a complete inventory of all assets in the S3 bucket.

Actions:

Run S3 inventory report (use AWS S3 Inventory or aws s3api list-objects-v2)

Export full file listing with: key (path), size, last modified, storage class, content type

Calculate total volume: number of objects, total size in GB/TB

Identify asset distribution by file extension/type

Identify folder structure depth and breadth

Flag oversized assets (>2GB) requiring special handling

Identify duplicate assets (same hash, different paths)

Sample AWS CLI Commands:

aws s3api list-objects-v2 --bucket <bucket-name> --output json > s3_inventory.json

aws s3 ls s3://<bucket-name>/ --recursive --summarize > s3_listing.txt

## Step 1.2: Asset Type Analysis

| Category | Extensions | Special Handling |
| --- | --- | --- |
| Images | JPG, PNG, GIF, SVG, WebP, TIFF, PSD, AI | Renditions auto-generated; check color profiles |
| Documents | PDF, DOCX, XLSX, PPTX | Full-text indexing enabled in AEM |
| Videos | MP4, MOV, AVI, MKV, WebM | Dynamic Media transcoding if enabled; size limits apply |
| 3D Assets | GLB, GLTF, OBJ, FBX | Requires 3D asset support enabled in AEMaaCS |
| Audio | MP3, WAV, FLAC, AAC | Basic metadata extraction |
| Archives | ZIP, RAR, TAR | Decide: extract or store as-is |
| Creative | INDD, SKETCH, FIG | Limited preview support in AEM |

## Step 1.3: Metadata Source Assessment

Goal: Understand the external metadata database/CSV structure and its linkage to S3 assets.

Identify the metadata source system (database type, CSV location, API endpoint)

Document the join key between metadata and S3 assets (filename, asset ID, path, UUID)

Export sample metadata records (100-500 assets) for analysis

Catalog all metadata fields: name, data type, cardinality, required/optional

Identify metadata quality issues: missing values, inconsistent formats, duplicates

Determine which metadata fields map to standard AEM properties vs. custom schema

Check for multi-value fields, hierarchical tags, and relational metadata

## Step 1.4: Assessment Deliverables

| Deliverable | Description | Owner |
| --- | --- | --- |
| S3 Inventory Report | Complete file listing with size, type, path analysis | Migration Engineer |
| Asset Volume Summary | Total count, size, breakdown by type and folder | Migration Engineer |
| Metadata Field Catalog | All source metadata fields with types and mapping candidates | Metadata Analyst |
| Source Folder Tree | Visual/textual representation of current S3 folder structure | Migration Engineer |
| Risk & Exception Log | Oversized files, special characters, duplicates, corrupt files | Migration Lead |
| Migration Sizing Estimate | Estimated duration, batch sizes, infrastructure needs | Solution Architect |

# Phase 2: Target DAM Structure Design

Objective: Design the target folder structure in AEM DAM that supports governance, findability, performance, and scalability.

## Step 2.1: DAM Taxonomy Design Principles

Principle 1: Flat over deep — minimize folder depth (max 4-5 levels recommended for AEMaaCS performance)

Principle 2: Metadata over folders — use metadata/tags for classification rather than deep folder nesting

Principle 3: Governance boundaries — folder structure should align with permission/access boundaries

Principle 4: Scalability — no more than 1,000-2,000 direct children per folder for optimal performance

Principle 5: Naming conventions — consistent, lowercase, hyphenated folder names (no spaces or special characters)

## Step 2.2: Target Structure Template

Example target DAM structure:

/content/dam/

├── brand-assets/

│   ├── logos/

│   ├── guidelines/

│   └── templates/

├── marketing/

│   ├── campaigns/

│   ├── social-media/

│   └── email/

├── product-assets/

│   ├── product-images/

│   ├── datasheets/

│   └── videos/

├── corporate/

│   ├── leadership/

│   ├── events/

│   └── press/

└── shared/

├── stock-images/

├── icons/

└── templates/

## Step 2.3: Folder Permissions Design

| Folder | Read Access | Write Access | Admin |
| --- | --- | --- | --- |
| /content/dam/brand-assets | All authors | Brand team only | DAM Admin |
| /content/dam/marketing | All authors | Marketing team | Marketing Lead |
| /content/dam/product-assets | All authors | Product team | Product Lead |
| /content/dam/corporate | All authors | Corporate comms | Corp Lead |
| /content/dam/shared | All authors | All authors | DAM Admin |

## Step 2.4: Metadata Schema Design (AEM)

Define the target metadata schema in AEM DAM:

| Field Name | AEM Property | Type | Required | Source |
| --- | --- | --- | --- | --- |
| Title | dc:title | Text | Yes | CSV/DB field: title |
| Description | dc:description | Textarea | No | CSV/DB field: description |
| Keywords/Tags | cq:tags | Tag (multi) | No | CSV/DB field: keywords |
| Category | dam:category | Dropdown | Yes | Derived from folder path |
| Brand | custom:brand | Dropdown | No | CSV/DB field: brand |
| Region | custom:region | Dropdown | No | CSV/DB field: region |
| Expiry Date | prism:expirationDate | Date | No | CSV/DB field: expiry_date |
| Usage Rights | xmpRights:UsageTerms | Text | No | CSV/DB field: license_type |
| Source System ID | custom:sourceId | Text (hidden) | Yes | CSV/DB field: asset_id |

Note: Create custom metadata schema in AEM before migration. Navigate to: Tools > Assets > Metadata Schemas to configure.

# Phase 3: Folder Mapping Rules Definition

Objective: Define the rule-based transformation logic that converts S3 source paths to AEM DAM target paths.

## Step 3.1: Transformation Rule Types

| Rule Type | Description | Example |
| --- | --- | --- |
| Rename | Change folder name at specific level | /images/hero_banners/ → /content/dam/marketing/hero-banners/ |
| Flatten | Remove intermediate folder levels | /assets/2024/Q1/Jan/images/ → /content/dam/marketing/2024/ |
| Merge | Combine multiple source folders into one target | /photos/ + /pictures/ → /content/dam/product-assets/product-images/ |
| Split | Distribute contents of one folder to multiple targets | /all-assets/ → split by type to /images/, /docs/, /videos/ |
| Prefix/Suffix | Add path prefix or suffix | /campaign-x/ → /content/dam/marketing/campaigns/campaign-x/ |
| Regex Replace | Pattern-based path transformation | /[YEAR]_[MONTH]/ → /[YEAR]/ (flatten month level) |
| Conditional | Route based on file type or metadata | IF .pdf THEN /documents/ ELSE /images/ |

## Step 3.2: Define Mapping Rules Document

Create a structured mapping rules document (CSV or JSON):

| Rule ID | Source Pattern | Target Path | Rule Type | Condition | Priority |
| --- | --- | --- | --- | --- | --- |
| R001 | /brand/logos/* | /content/dam/brand-assets/logos/ | Rename + Prefix | None | 1 |
| R002 | /marketing/*/banners/* | /content/dam/marketing/campaigns/{1}/banners/ | Restructure | None | 2 |
| R003 | /products/*/images/* | /content/dam/product-assets/product-images/{1}/ | Flatten | None | 3 |
| R004 | /archive/**/*.pdf | /content/dam/corporate/archived-docs/ | Merge + Flatten | Extension = .pdf | 4 |
| R005 | /temp/* | [EXCLUDE] | Exclude | None | 5 |
| R006 | /**/*.psd | /content/dam/shared/source-files/ | Conditional | Extension = .psd | 6 |
| R007 | /**/thumbnails/* | [EXCLUDE] | Exclude | Folder name = thumbnails | 7 |

## Step 3.3: Rule Processing Logic

Rules are processed in priority order. The first matching rule determines the target path:

Load all assets from S3 inventory

For each asset, iterate rules by priority (1 = highest)

Apply the first matching rule to generate target path

If no rule matches, apply default rule (configurable: exclude, or map to /content/dam/unmapped/)

Validate target path against AEM constraints (length, characters, depth)

Log any assets that fail validation for manual review

Output: source-to-target mapping CSV for execution

## Step 3.4: Sample Transformation Script (Python)

import re, csv

rules = [
    {"id": "R001", "pattern": r"^/brand/logos/(.+)$",
     "target": "/content/dam/brand-assets/logos/{0}"},
    {"id": "R002", "pattern": r"^/marketing/([^/]+)/banners/(.+)$",
     "target": "/content/dam/marketing/campaigns/{0}/banners/{1}"},
    {"id": "R005", "pattern": r"^/temp/.*$",
     "target": None},  # Exclude
    # Default catch-all
    {"id": "DEFAULT", "pattern": r"^/(.+)$",
     "target": "/content/dam/migrated/{0}"},
]

def transform_path(source_path):
    for rule in rules:
        match = re.match(rule["pattern"], source_path)
        if match:
            if rule["target"] is None:
                return None  # Excluded
            groups = match.groups()
            return rule["target"].format(*groups)
    return None

## Step 3.5: Deliverables

Folder mapping rules document (CSV/JSON) — reviewed and approved by stakeholders

Transformation script (tested against full inventory)

Source-to-target mapping output (complete CSV: source_path → target_path)

Exclusion list (assets intentionally not migrated, with justification)

Exception report (assets that failed rule matching or validation)

# Phase 4: Metadata Mapping & Transformation

Objective: Map source metadata fields to AEM DAM properties, transform values, and prepare metadata import files.

## Step 4.1: Metadata Field Mapping

Create a comprehensive field-by-field mapping:

| Source Field | Source Type | AEM Property Path | AEM Type | Transformation |
| --- | --- | --- | --- | --- |
| asset_id | VARCHAR(50) | jcr:content/metadata/custom:sourceId | String | Direct copy |
| title | VARCHAR(255) | jcr:content/metadata/dc:title | String | Trim whitespace |
| description | TEXT | jcr:content/metadata/dc:description | String | Truncate to 2000 chars |
| keywords | VARCHAR(500) | jcr:content/metadata/cq:tags | String[] | Split by comma; map to AEM tag paths |
| created_date | DATETIME | jcr:content/metadata/dam:assetCreated | Date | Convert to ISO 8601 |
| author | VARCHAR(100) | jcr:content/metadata/dc:creator | String | Direct copy |
| license | VARCHAR(50) | jcr:content/metadata/xmpRights:UsageTerms | String | Map values: 1=RF, 2=RM, 3=CC |
| expiry | DATE | jcr:content/metadata/prism:expirationDate | Date | Convert to ISO 8601; null if empty |
| brand_name | VARCHAR(100) | jcr:content/metadata/custom:brand | String | Normalize to lowercase |
| region_code | VARCHAR(10) | jcr:content/metadata/custom:region | String | Map code to full name: US=North America |

## Step 4.2: Metadata Transformation Rules

Extract: Extract metadata from source database/CSV for all assets in migration scope

Join: Join metadata to asset inventory using the linkage key (filename, asset_id, or path)

Transform: Apply field-level transformations (type conversion, value mapping, formatting)

Validate: Validate transformed metadata against AEM schema constraints

Generate: Generate AEM-compatible metadata CSV files (one per batch or folder)

## Step 4.3: AEM Metadata CSV Format

AEMaaCS Bulk Import accepts metadata via CSV sidecar files. Required format:

assetPath,dc:title,dc:description,cq:tags,custom:brand,custom:region
/content/dam/marketing/hero.jpg,"Hero Banner","Main campaign hero",campaign:2024|type:banner,acme,north-america
/content/dam/products/widget.png,"Widget Photo","Product shot",product:widget|type:photo,acme,global

Note: Multi-value fields use pipe (|) as delimiter. Tag values must match existing AEM tag paths. Create tag taxonomy in AEM before import.

## Step 4.4: Tag Taxonomy Preparation

Extract unique tag/keyword values from metadata source

Design AEM tag namespace and hierarchy (e.g., properties:brand/acme, properties:region/na)

Create tag mapping: source_value → AEM_tag_path

Pre-create tags in AEM via Tag Admin or ACS Commons Tag Creator

Validate all tag references in metadata CSV resolve to existing AEM tags

## Step 4.5: Handling Missing & Orphan Metadata

| Scenario | Action |
| --- | --- |
| Asset exists in S3 but no metadata record | Migrate asset with minimal metadata (title from filename); flag for manual enrichment |
| Metadata record exists but no S3 asset | Log as orphan metadata; do not create empty DAM entries |
| Multiple metadata records for one asset | Apply merge logic (latest wins, or concatenate for multi-value fields) |
| Metadata field value exceeds AEM limit | Truncate with logging; flag for review |
| Metadata contains HTML/special characters | Strip HTML tags; escape special characters |

# Phase 5: Migration Tooling & Infrastructure Setup

Objective: Set up the technical infrastructure and tooling required to execute the migration.

## Step 5.1: Choose Migration Approach

| Approach | Best For | Pros | Cons |
| --- | --- | --- | --- |
| AEMaaCS Bulk Import (Native) | Large-scale, straightforward migrations | Native tool; S3 connector; parallel processing; metadata CSV support | Limited transformation during import; requires pre-staged structure |
| Custom Migration Script + AEM Assets API | Complex transformations; metadata-heavy | Full control; real-time transformation; API metadata write | Slower; requires development; rate limiting |
| Hybrid: Pre-stage in S3 + Bulk Import | Large-scale with restructuring | Best of both; bulk speed with custom transform | Requires staging bucket; two-phase process |
| Third-Party Tools (e.g., MigrateAEM, CloudSmith) | Turnkey solution needed | GUI-based; built-in validation | Cost; vendor dependency; may not fit custom rules |

Recommended Approach: Hybrid — Pre-stage assets in a new S3 bucket with target folder structure applied, then use AEMaaCS native Bulk Import for ingestion with metadata CSV sidecar files.

## Step 5.2: Infrastructure Requirements

| Component | Purpose | Specification |
| --- | --- | --- |
| Staging S3 Bucket | Hold restructured assets before AEM import | Same region as AEM; lifecycle policy for cleanup |
| Migration Server (EC2) | Run transformation scripts | r5.xlarge or larger; SSD; same VPC as S3 |
| AEMaaCS Environment | Target DAM instance | Dev/Stage for testing; Prod for final migration |
| Database Access | Read metadata source | Read-only credentials; VPN/direct connect if needed |
| Logging & Monitoring | Track migration progress | CloudWatch + custom dashboard |
| Network | High-throughput data transfer | S3 Transfer Acceleration or VPC endpoint |

## Step 5.3: AEMaaCS Bulk Import Configuration

Navigate to AEM Author > Tools > Assets > Bulk Import

Create new import configuration:

Title: "S3 Asset Migration - [Batch Name]"

Import Source: Amazon S3

S3 Bucket: [staging-bucket-name]

S3 Region: [region]

Access Key / Secret Key: [IAM credentials with s3:GetObject, s3:ListBucket]

Source Folder: / (or specific prefix)

Target Folder: /content/dam/

Import Mode: Replace (or Skip existing)

Apply Metadata: Yes (CSV file reference)

Set up IAM policy for AEM access (minimum: s3:GetObject, s3:ListBucket on staging bucket)

Test connectivity with a small sample (10 assets)

Configure processing profiles if needed (video transcoding, image renditions)

## Step 5.4: Staging Pipeline Script Architecture

Build an automated pipeline for the staging phase:

Step 1: Read S3 inventory from source bucket

Step 2: Apply folder transformation rules → generate target paths

Step 3: Copy assets from source S3 to staging S3 with new folder structure

Step 4: Extract metadata from database/CSV

Step 5: Join metadata to assets via linkage key

Step 6: Apply metadata transformations

Step 7: Generate AEM metadata CSV sidecar files

Step 8: Upload metadata CSVs to staging bucket alongside assets

Step 9: Validate staging bucket structure matches expected target

Step 10: Trigger AEMaaCS Bulk Import

## Step 5.5: Environment Preparation Checklist

| # | Task | Status | Owner |
| --- | --- | --- | --- |
| 1 | Create staging S3 bucket with appropriate policies | [ ] | Cloud Engineer |
| 2 | Set up migration EC2 instance with tooling | [ ] | DevOps |
| 3 | Configure IAM roles/credentials for S3 access | [ ] | Cloud Engineer |
| 4 | Create AEM metadata schema (custom fields) | [ ] | AEM Developer |
| 5 | Create AEM tag taxonomy | [ ] | AEM Developer |
| 6 | Configure AEM processing profiles | [ ] | AEM Developer |
| 7 | Set up AEM user groups and folder permissions | [ ] | AEM Admin |
| 8 | Create target folder structure in AEM DAM | [ ] | AEM Admin |
| 9 | Obtain database read credentials for metadata | [ ] | DBA |
| 10 | Test network connectivity: EC2 → S3 → AEM | [ ] | DevOps |

# Phase 6: Pre-Migration Validation & Dry Run

Objective: Validate the complete migration pipeline end-to-end with a representative sample before executing at full scale.

## Step 6.1: Select Validation Sample

500-1000 assets covering all asset types

Assets from multiple source folders (testing all mapping rules)

Include edge cases: long filenames, special characters, large files, missing metadata

Include assets that hit every transformation rule

## Step 6.2: Dry Run Execution

Execute transformation pipeline on sample set

Verify folder mapping output matches expected paths

Verify metadata CSV generation is correct

Stage sample assets in staging S3 bucket

Execute Bulk Import to AEM Dev/Stage environment

Validate results against checklist (Step 6.3)

## Step 6.3: Validation Checklist

| # | Check | Expected Result | Pass/Fail |
| --- | --- | --- | --- |
| 1 | All sample assets appear in correct AEM DAM folder | 100% match to target path mapping | [ ] |
| 2 | Asset filenames preserved correctly | No encoding issues, truncation, or character loss | [ ] |
| 3 | Metadata fields populated on assets | All mapped fields present with correct values | [ ] |
| 4 | Tags resolved correctly | All tag references link to valid AEM tags | [ ] |
| 5 | Renditions generated for images | Standard renditions auto-created by AEM | [ ] |
| 6 | Video assets processed | Transcoding profiles applied (if Dynamic Media enabled) | [ ] |
| 7 | No duplicate assets created | Each asset exists exactly once at target path | [ ] |
| 8 | Excluded assets NOT imported | Temp/excluded files absent from AEM | [ ] |
| 9 | Folder permissions correct | ACLs applied as designed | [ ] |
| 10 | Asset search works with metadata | Can find assets via metadata search in AEM | [ ] |
| 11 | No path length violations | All paths under 350 characters | [ ] |
| 12 | Performance acceptable | Import rate meets timeline requirements | [ ] |

## Step 6.4: Performance Benchmarking

During dry run, capture performance metrics:

| Metric | Measurement | Target |
| --- | --- | --- |
| S3 copy throughput | Assets/minute from source to staging | >500 assets/min |
| AEM import throughput | Assets/minute ingested by Bulk Import | >100 assets/min |
| Metadata application rate | Metadata records applied per minute | >200 records/min |
| Error rate | % of assets failing import | <0.5% |
| End-to-end time (sample) | Total time for sample batch | Baseline for extrapolation |

Note: Use benchmarks to calculate total migration duration and plan batch sizing. Factor in AEM processing queues (workflows, renditions) which may throttle sustained import rates.

# Phase 7: Migration Execution

Objective: Execute the full-scale migration in controlled batches with monitoring and rollback capability.

## Step 7.1: Batch Strategy

Divide the total asset corpus into manageable batches:

| Consideration | Recommendation |
| --- | --- |
| Batch size | 5,000 - 20,000 assets per batch (adjust based on dry run throughput) |
| Batch grouping | Group by target folder OR by source folder (maintains logical units) |
| Batch sequence | Start with lowest-risk/simplest content; escalate to complex/high-visibility |
| Parallel batches | Max 2-3 concurrent Bulk Import jobs (avoid AEM processing queue saturation) |
| Off-peak scheduling | Run batches during off-peak hours to minimize impact on authors |
| Checkpoint frequency | Validate after each batch before proceeding to next |

## Step 7.2: Execution Sequence

Step A: Pre-Flight Check: Confirm AEM environment is healthy; no pending deployments or maintenance windows

Step B: Stage Batch: Run transformation pipeline for batch N; copy to staging S3 with metadata CSVs

Step C: Import: Trigger AEMaaCS Bulk Import for batch N

Step D: Monitor: Track import progress via AEM Bulk Import UI; watch for errors in logs

Step E: Validate: Run automated validation checks on imported batch (spot checks + counts)

Step F: Checkpoint: Compare expected vs. actual asset counts; verify sample metadata; log issues

Step G: Proceed or Remediate: If pass → next batch. If fail → pause, investigate, fix, re-run batch.

## Step 7.3: Monitoring Dashboard

Track these metrics during execution:

Assets imported (count + rate per minute)

Assets failed (count + error type breakdown)

AEM repository size growth

AEM workflow queue depth (rendition generation)

Staging bucket status (pending vs. completed)

Elapsed time vs. projected timeline

Error log entries (categorized)

## Step 7.4: Error Handling & Recovery

| Error Type | Cause | Resolution |
| --- | --- | --- |
| Import timeout | Large file or network issue | Retry individual asset via API; increase timeout settings |
| Path conflict | Asset already exists at target | Apply duplicate handling policy (skip/overwrite/version) |
| Invalid metadata | Bad value or missing required field | Fix in metadata CSV; re-import affected assets only |
| Quota exceeded | AEM storage limit hit | Contact Adobe support; request quota increase; pause migration |
| Processing backlog | Rendition queue overwhelmed | Pause imports; wait for queue to drain; reduce batch parallelism |
| Network failure | Connectivity interruption | Resume from last checkpoint; Bulk Import supports resume |

## Step 7.5: Rollback Plan

Important: Define rollback triggers and procedures before starting execution.

Trigger 1: If error rate exceeds 5%: Pause all imports, investigate root cause

Trigger 2: If AEM becomes unresponsive: Stop all imports, engage Adobe support

Trigger 3: If incorrect assets imported to wrong location: Use AEM bulk move/delete via API

Rollback actions:

Stop all in-progress Bulk Import jobs

Identify scope of incorrect imports (which batches affected)

Delete incorrectly imported assets from AEM (via API or Move to Archive)

Fix root cause in pipeline/rules

Re-run affected batches from staging

# Phase 8: Post-Migration Validation & QA

Objective: Comprehensive validation that all assets are correctly migrated, accessible, and enriched with metadata.

## Step 8.1: Automated Validation

Check 1: Asset Count Reconciliation: S3 source count (minus exclusions) = AEM DAM count

Check 2: Path Verification: Sample 1% of assets; verify each is at expected target path

Check 3: Metadata Completeness: Query AEM for assets missing required metadata fields

Check 4: File Integrity: Compare file sizes (source vs. imported original rendition)

Check 5: Rendition Generation: Verify processing profiles applied; renditions exist

Check 6: Tag Resolution: Confirm all tag references resolve; no broken tags

Check 7: Permission Validation: Test folder access with different user roles

Check 8: Search Validation: Perform metadata searches; confirm findability

## Step 8.2: Manual QA Sampling

| QA Area | Method | Sample Size |
| --- | --- | --- |
| Visual integrity | Open assets in AEM preview; compare to S3 original | 50-100 assets across types |
| Metadata accuracy | Manual spot-check of metadata values against source DB | 100 assets (random) |
| Folder structure | Navigate DAM tree; verify organizational logic | All top-level folders |
| Download & usability | Download assets from AEM; verify file opens correctly | 20-30 assets per type |
| Video playback | Play migrated videos in AEM player | 10-20 videos |
| Search experience | Author searches for assets by various criteria | 20 search scenarios |

## Step 8.3: Discrepancy Resolution

Generate discrepancy report (missing assets, metadata mismatches, path errors)

Categorize discrepancies by severity (Critical / Major / Minor)

Critical: missing assets, wrong content → immediate re-import

Major: incorrect metadata, wrong folder → batch correction via API

Minor: formatting issues, optional metadata gaps → backlog for post-migration cleanup

Re-run validation after corrections; iterate until acceptance criteria met

## Step 8.4: Acceptance Criteria

| Criterion | Threshold | Measurement |
| --- | --- | --- |
| Asset count accuracy | >99.5% of source assets present in AEM | Count comparison |
| Metadata completeness | >98% of assets have all required fields populated | AEM query |
| Path accuracy | 100% of sampled assets at correct target path | Sample validation |
| File integrity | 100% of sampled assets match source file size | Size comparison |
| Search functionality | All test search scenarios return expected results | Manual testing |
| Performance | AEM Author UI responsive; no degradation | User experience testing |

# Phase 9: Cutover & Go-Live

Objective: Transition from S3 as the asset source to AEM DAM as the system of record.

## Step 9.1: Delta Migration

Handle assets added/modified in S3 between migration start and cutover:

Identify delta: assets created or modified in S3 after initial migration snapshot

Run transformation pipeline on delta assets only

Import delta batch to AEM (smaller, faster execution)

Validate delta imports

Repeat until delta window is small enough for final cutover (<1 hour)

## Step 9.2: Cutover Checklist

| # | Task | Timing | Owner |
| --- | --- | --- | --- |
| 1 | Freeze S3 writes (communicate to all S3 producers) | T-24h | Project Manager |
| 2 | Run final delta migration | T-4h | Migration Engineer |
| 3 | Final validation pass | T-2h | QA Team |
| 4 | Update application references from S3 URLs to AEM DAM URLs | T-1h | Development Team |
| 5 | Configure CDN/redirects from old S3 URLs to AEM delivery URLs | T-1h | DevOps |
| 6 | Enable AEM DAM for authors (remove read-only restrictions) | T-0 | AEM Admin |
| 7 | Smoke test: authors access and use migrated assets | T+15min | QA Team |
| 8 | Monitor for 404s / broken references in downstream systems | T+1h | DevOps |
| 9 | Communicate go-live to stakeholders | T+1h | Project Manager |
| 10 | Retain S3 bucket in read-only mode for 30 days (rollback safety net) | T+0 to T+30d | Cloud Engineer |

## Step 9.3: URL Redirect Strategy

If assets were served directly from S3 via CloudFront or public URLs, implement redirects:

| Old URL Pattern | New URL Pattern | Method |
| --- | --- | --- |
| https://cdn.example.com/assets/... | https://author.aem.cloud/content/dam/... | CDN redirect rule or Lambda@Edge |
| s3://bucket/path/asset.jpg | /content/dam/target/path/asset.jpg | Application code update |
| https://s3.region.amazonaws.com/bucket/... | AEM Dynamic Media URL | CloudFront behavior + redirect |

## Step 9.4: Post-Go-Live Monitoring (2 weeks)

Monitor 404 rates on old asset URLs (should be near zero with redirects)

Track AEM DAM usage metrics (asset downloads, searches, author activity)

Watch AEM performance (repository size growth, query performance)

Collect author feedback on findability and usability

Address any escalated discrepancies from post-migration QA backlog

## Step 9.5: Decommission Plan

| Milestone | Action | Timing |
| --- | --- | --- |
| T+7 days | Review redirect/404 logs; confirm no critical dependencies on S3 | Week 1 |
| T+14 days | Remove write access to legacy S3 bucket | Week 2 |
| T+30 days | Move S3 bucket to Glacier/cold storage (cost reduction, backup retention) | Month 1 |
| T+90 days | Final review; delete S3 bucket if no longer needed | Month 3 |
| T+90 days | Decommission migration infrastructure (EC2, staging bucket) | Month 3 |

# Appendix A: AEMaaCS Bulk Import Configuration Reference

AEMaaCS native Bulk Import supports direct ingestion from AWS S3:

| Setting | Value | Notes |
| --- | --- | --- |
| Import Source | Amazon S3 | Also supports Azure Blob Storage |
| S3 Bucket Name | [your-staging-bucket] | Must be accessible from AEM Cloud |
| S3 Region | [e.g., us-east-1] | Match AEM program region for best performance |
| Access Key ID | [IAM user key] | Minimum: s3:GetObject, s3:ListBucket |
| Secret Access Key | [IAM secret] | Use dedicated migration IAM user |
| Source Folder | / | S3 prefix to import from |
| Target AEM Folder | /content/dam/ | Must exist in AEM before import |
| Overwrite Mode | Skip / Replace / Create Version | Choose based on migration phase |
| Ignore Folders | .tmp, _processing | Comma-separated folders to skip |
| Mime Type Filter | (optional) | e.g., image/* to import only images |
| Metadata CSV | [path-to-csv-in-s3] | CSV with assetPath + metadata columns |

## IAM Policy (Minimum Required)

{
  "Version": "2012-10-17",
  "Statement": [
    {
      "Effect": "Allow",
      "Action": [
        "s3:GetObject",
        "s3:ListBucket"
      ],
      "Resource": [
        "arn:aws:s3:::your-staging-bucket",
        "arn:aws:s3:::your-staging-bucket/*"
      ]
    }
  ]
}

# Appendix B: Metadata Schema Reference

Standard AEM DAM metadata namespaces:

| Namespace | Prefix | Common Properties |
| --- | --- | --- |
| Dublin Core | dc: | title, description, creator, subject, rights, format |
| XMP Rights | xmpRights: | UsageTerms, WebStatement, Owner |
| PRISM | prism: | expirationDate, aggregationType |
| DAM | dam: | relativePath, sha1, size, extracted |
| CQ | cq: | tags, lastModified, lastReplicated |
| Custom | custom: | Any project-specific fields (define in schema editor) |

# Appendix C: Troubleshooting Guide

| Issue | Likely Cause | Resolution |
| --- | --- | --- |
| Bulk Import fails to connect to S3 | IAM credentials incorrect or bucket policy blocks access | Verify IAM key/secret; check bucket policy allows GetObject from AEM IPs |
| Import hangs on large files | Timeout on files >5GB | Use multipart upload to staging; consider chunking; contact Adobe support for timeout settings |
| Metadata not applied | CSV format incorrect or assetPath mismatch | Verify CSV column names match AEM property paths; ensure assetPath matches imported path exactly |
| Tags show as unresolved | Tag paths in CSV don't match AEM tag taxonomy | Pre-create all tags in AEM; verify exact path match including namespace |
| Renditions not generating | Processing profiles not configured or queue backed up | Check processing profile assignment; monitor workflow queue; wait for backlog to clear |
| Duplicate assets | Import mode set to "Create Version" with same filename | Set to "Skip" for re-runs; use "Replace" for updates |
| AEM slow after large import | Oak index rebuilding; large number of pending workflows | Wait for background indexing; pause workflows if needed; contact Adobe support |
| Permission denied on import | AEM service user lacks write access to target folder | Verify AEM user permissions; check rep:policy nodes on target folders |

— End of Document —