## GA4 Tracker
Google Analytics GA4 and Digital Tracking Tracker for GSM Adobe Commerce site
Purpose of this document is to track the development of the GA4 Tagging Plans for the different pages on the GSM Adobe Commerce website. The dependency is on the Phase 1 deliverable of wireframes and the Block definitions from the Adobe team.
See Design Tracker for the most current Figma links
| Page | Status of Tagging Plan Delivery | Wireframe (Adobe team) | Block Diagram (Adobe team) | Draft Tagging Plan Delivery Date (Digital Tracking team) | Tagging Plan Review Date (GSM teams) | Finalized plan Delivery Date (Digital Tracking team) | Approvers | Tagging Plan link
| Home Page - B2C, B2B, Leaders | complete | Yes | Yes | 2026-02-25 | 2026-02-25 | 2026-05-15 | GSM Business, Product teams | ACCS Tagging Plan - homepage - consumer - wholesale - leaders.docx
| PLP + Quick Add B2B | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - B2B List.docx
| PLP + Quick Add B2C | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - PLP Product Listings.docx
| Thank You Page | complete | Yes | Yes | 2026-03-11 | 2026-03-24 | 2026-06-05 |  | ACCS Tagging Plan - Thank You Page.docx
| Transaction and Invoice | complete | Yes | Yes | 2026-03-11 | 2026-03-24 | 2026-06-05 |  | ACCS Tagging Plan - Transaction and Invoice.docx
| Store Locator | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - Store Locator.docx
| Global Items | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - global items.docx
| PDP Product Detail | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - PDP Product Detail.docx
| Mini Cart | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - MiniCart.docx
| My Account | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - MyAccount.docx
| Contact Us | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - Contact Us.docx
| FAQ | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - FAQ.docx
| Fulfilment Log | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - Fulfilment Log.docx
| Council Landing Page | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - Council Landing Page.docx
| Wishlist B2C | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - B2C Wishlist.docx
| Checkout | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - Checkout.docx
| Orders B2B | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - B2B Orders.docx
| Quick Orders B2B | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - B2B QuickOrders.docx
| Cart | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - Cart.docx
| Lists B2B | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - B2B PLP + Quick Add.docx
| Account Overview B2B | complete | Yes | Yes |  |  | 2026-06-05 |  | ACCS Tagging Plan - B2B Account Overview.docx
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not Started, In Progress, In Review, Complete