# Cutover & Validation Strategy

Thermo Fisher Scientific — AEM 6.4 to EDS/DA Migration

# 1. Executive Summary

This document defines the cutover and validation strategy for migrating Thermo Fisher Scientific's web properties from AEM 6.4 (on-premise, AWS-hosted) to AEM Edge Delivery Services with Document Authoring (DA). The strategy ensures zero data loss, minimal disruption to end users, and measurable validation gates at every stage.

The cutover follows a phased, wave-based approach aligned with the migration strategy — progressing from global/en through regional hubs, country sites, and translated locales. Each wave has explicit entry criteria, validation checkpoints, and rollback triggers.

# 2. Cutover Approach

## 2.1 Phased Wave Model

The cutover follows the same wave structure as the content migration strategy:

| Wave | Scope | Content Types | Duration (Est.) | Dependencies |
| --- | --- | --- | --- | --- |
| Wave 0 | Infrastructure Setup | DA MSM structure, GitHub repos, EDS config, Edge Worker setup | 2-3 weeks | IMS/Identity config complete; GitHub access provisioned |
| Wave 1 | global/en (Baseline) | Global pages, XF fragments, forms XFs, syndication pods (global) | 3-4 weeks | Wave 0 complete; XF mapping table validated |
| Wave 2 | Regional EN Hubs | north-america/en, europe/en, ipac/en, japan/en, greater-china/en — delta pages only | 2-3 weeks per hub | Wave 1 live; MSM inheritance validated |
| Wave 3 | Country EN Sites | north-america/en-us, europe/en-gb, ipac/en-in, etc. — delta pages only | 2-3 weeks per batch | Wave 2 live; delta identification scripts run |
| Wave 4 | Translated Locales | de-de, fr-fr, ja-jp, zh-cn, ko-kr, etc. — ALL pages (sitemap-based) | 3-4 weeks per batch | Wave 3 live; sitemap crawl complete |
| Wave 5 | Syndication Pods & Commerce | Content syndication pods cutover to aem-embed | 2-3 weeks | Pod pilot (single SKU) validated with commerce team |

## 2.2 Cutover Flow Diagram

┌─────────────────────────────────────────────────────────────────────────────────────┐
│                          CUTOVER FLOW PER WAVE                                      │
├─────────────────────────────────────────────────────────────────────────────────────┤
│                                                                                     │
│  ┌──────────┐    ┌──────────┐    ┌──────────┐    ┌──────────┐    ┌──────────┐     │
│  │  ENTRY   │    │ MIGRATE  │    │ VALIDATE │    │  SWITCH  │    │ MONITOR  │     │
│  │ CRITERIA │───▶│ CONTENT  │───▶│  & TEST  │───▶│  TRAFFIC │───▶│& CONFIRM │     │
│  └──────────┘    └──────────┘    └──────────┘    └──────────┘    └──────────┘     │
│       │                │                │               │               │           │
│       ▼                ▼                ▼               ▼               ▼           │
│  • Prerequisites    • Run scripts    • Automated     • DNS/CDN       • 72-hour     │
│    met              • Push to DA       checks          switch          soak         │
│  • Prior wave       • Verify page    • Manual QA    • Redirect      • SEO check   │
│    stable             count          • SEO audit      activation    • Traffic      │
│  • Rollback plan   • Redirects      • Performance  • Old AEM         compare     │
│    documented        uploaded         test            fallback      • Incident     │
│                                      • Stakeholder    remains         review      │
│                                        sign-off                                    │
│                                                                                     │
│  ┌──────────────────────────────────────────────────────────────────────────────┐  │
│  │  ROLLBACK TRIGGER: Any P1 issue → revert DNS → AEM serves → investigate     │  │
│  └──────────────────────────────────────────────────────────────────────────────┘  │
│                                                                                     │
└─────────────────────────────────────────────────────────────────────────────────────┘

## 2.3 Parallel Run / Coexistence Period

During migration, both AEM 6.4 and EDS serve content simultaneously:

AEM 6.4 continues serving all unmigrated pages at production URLs.

EDS serves migrated pages at .aem.page (preview) and .aem.live (production) URLs during validation.

DNS/CDN switching is per-path or per-locale — not big-bang. Traffic is routed to EDS only for validated paths.

AEM 6.4 remains available as an instant rollback target for the duration of each wave's soak period.

Authors can continue editing on AEM 6.4 for unmigrated pages — no authoring freeze for the full site.

Content freeze applies only to pages in the active migration wave (typically 1-2 weeks per wave).

# 3. Entry Criteria Per Wave

| Criterion | Wave 0 | Wave 1 | Wave 2-4 | Wave 5 (Pods) |
| --- | --- | --- | --- | --- |
| Prior wave validated and stable (72hr soak) | — | Wave 0 complete | Prior wave stable | Wave 3+ stable |
| Page/content list approved by TFS | — | Global page inventory confirmed | Delta page list approved | Pod SKU list confirmed |
| Rollback plan documented and tested | Yes | Yes | Yes | Yes |
| Content freeze in effect for wave scope | — | Global/en freeze | Locale freeze | Pod content freeze |
| Migration scripts tested on staging | N/A | Dry run on staging | Dry run per locale | Pilot SKU validated |
| Redirect spreadsheet uploaded and validated | — | Global redirects | Locale redirects | Pod URL mappings |
| Stakeholder sign-off to proceed | Architecture lead | TFS content + dev | Regional content team | Commerce team |

# 4. Validation Strategy

## 4.1 Validation Layers

Validation is performed at four layers, each catching different categories of issues:

| Layer | What It Validates | When | Tool / Method | Pass Criteria |
| --- | --- | --- | --- | --- |
| L1 — Automated Pipeline | Page count, block rendering, broken links, image loading | During migration (per page) | Migration script validation + EDS preview | 100% pages created; zero broken internal links |
| L2 — SEO & Performance | Metadata parity, redirects, CWV scores, structured data | Post-migration (per wave) | Lighthouse CI, Screaming Frog, Schema Validator | Lighthouse ≥95; all redirects 301; no missing metadata |
| L3 — Visual & Functional QA | Visual fidelity, block interactions, responsive behavior, forms | Post-migration (per wave) | Manual QA + Playwright/Puppeteer automated visual | No P1/P2 visual defects; all forms submit correctly |
| L4 — Production Monitoring | Real user metrics, error rates, traffic patterns, SEO impact | Post-cutover (72hr soak) | RUM, Google Search Console, Analytics, error logs | No traffic drop >5%; zero P1 errors; CWV in green |

## 4.2 L1 — Automated Pipeline Validation

Every page migrated by the pipeline undergoes automated validation:

| Check | Description | Failure Action |
| --- | --- | --- |
| Page creation verified | DA Admin API confirms page exists at expected path | Retry push; escalate if persistent |
| HTTP 200 on preview | Fetch .aem.page URL — must return 200 | Investigate missing page; check DA push logs |
| Block rendering | All block tables rendered to decorated DOM (no raw tables visible) | Check block JS errors; fix and re-deploy |
| Image loading | All <img> src attributes resolve to 200 responses | Fix broken image references; re-run transform |
| Internal link integrity | All internal <a href> links resolve to valid pages | Fix link paths in transform scripts |
| Metadata present | <title>, <meta description>, canonical URL present in <head> | Check metadata block in DA document |
| Form rendering (if form page) | tfs-form block detected and form fields render | Check JCR fetch + form transform output |
| Fragment loading (if fragments) | Fragment references load and render content | Verify fragment path mapping; check DA fragment exists |

## 4.3 L2 — SEO & Performance Validation

Run after all pages in a wave are migrated, before traffic switch:

| Check | Tool | Criteria | Scope |
| --- | --- | --- | --- |
| Lighthouse Performance | Lighthouse CI (automated) | Score ≥ 95 on sample pages per template type | 10-20 pages per template |
| Lighthouse SEO | Lighthouse CI | Score = 100 | All migrated pages (automated scan) |
| Core Web Vitals | PageSpeed Insights API | LCP < 2.5s, CLS < 0.1, INP < 200ms | Top 50 pages by traffic |
| Redirect validation | Screaming Frog / custom script | All source URLs → 301 → correct destination | 100% of redirect spreadsheet |
| Metadata parity | Custom crawler comparing old vs new | Title, description, canonical match or improve | 100% of migrated pages |
| Structured data | Google Rich Results Test / Schema Validator | No schema errors; same types as source | Pages with schema (FAQ, Product, Video, Breadcrumb) |
| Sitemap coverage | Compare sitemap.xml entries vs migrated page list | All migrated pages present in sitemap | 100% coverage |
| robots.txt | Manual check + fetch-as-Google | Production allows crawling; staging blocks | Per environment |
| Hreflang validation | Screaming Frog hreflang audit | Valid hreflang tags; correct locale mapping; return links present | All multi-locale pages |
| 404 error check | Crawl all internal links from migrated pages | Zero 404s on internal links | Full link graph |

## 4.4 L3 — Visual & Functional QA

Manual and automated QA to validate the end-user experience:

| Check Category | Checks Performed | Method |
| --- | --- | --- |
| Visual fidelity | Compare EDS page against AEM source — layout, spacing, colors, fonts, images | Side-by-side visual comparison (automated screenshot diff + manual review) |
| Block interactions | Accordion expand/collapse, tabs switching, carousel navigation, video play | Manual testing + Playwright E2E scripts |
| Responsive behavior | Verify at mobile (375px), tablet (768px), desktop (1440px) | Browser DevTools + BrowserStack/LambdaTest |
| Form submission | Fill and submit all form types; verify success message and backend receipt | Manual testing per form; verify Eloqua/backend receives data |
| Navigation | Header, footer, breadcrumb, sub-nav, anchor links all working | Manual navigation walkthrough + automated link check |
| Cross-browser | Chrome, Edge, Safari, Firefox — latest versions | BrowserStack automated matrix |
| Accessibility | Keyboard navigation, screen reader, color contrast, ARIA attributes | axe-core automated + manual NVDA/VoiceOver testing |
| Content parity | All text, images, links match source page content | Automated text diff + visual comparison |

## 4.5 L4 — Production Monitoring (72-Hour Soak)

After traffic switch, the wave enters a 72-hour soak period with active monitoring:

| Metric | Monitoring Tool | Alert Threshold | Escalation |
| --- | --- | --- | --- |
| Error rate (5xx) | EDS RUM / CDN logs | > 0.1% of requests | Immediate P1 — investigate; consider rollback |
| 404 rate | CDN logs + Search Console | > 1% of requests (new 404s) | Fix redirects immediately; add missing pages |
| Page load time (P75) | EDS RUM | LCP > 3.0s on any template | Investigate block; hotfix and re-deploy |
| Organic traffic | Google Analytics / Adobe Analytics | Drop > 10% vs prior week (same day-of-week) | SEO investigation; check indexing, redirects, canonicals |
| CWV field data | Chrome UX Report (CrUX) / RUM | Any metric moves from Good to Needs Improvement | Performance investigation |
| Form submissions | Backend monitoring / Eloqua | Drop > 20% vs prior week | Check form rendering; verify submission endpoints |
| Bounce rate | Analytics | Increase > 15% vs baseline | Visual/content issue investigation |
| Search Console coverage | Google Search Console | Indexed pages drop > 5% | Check robots.txt, sitemap, noindex tags |

# 5. Rollback Strategy

## 5.1 Rollback Triggers

A rollback is triggered if any of the following occur during or after cutover:

P1 defect affecting > 10% of migrated pages (e.g., broken rendering, missing content)

5xx error rate exceeds 0.5% for more than 15 minutes

Form submissions completely failing (zero submissions reaching backend)

Organic traffic drops > 20% within 48 hours with no external explanation

Commerce syndication pods not rendering on product pages (commerce team escalation)

Security vulnerability identified in new infrastructure

Stakeholder decision to halt based on business-critical user feedback

## 5.2 Rollback Procedure

Incident commander declares rollback decision (requires sign-off from TFS + Adobe lead).

CDN/DNS routing for affected paths reverted to AEM 6.4 origin (estimated time: 5-15 minutes depending on CDN TTL).

Confirm AEM 6.4 is serving affected pages correctly (spot-check 5 URLs across templates).

Notify all stakeholders (content team, SEO, commerce, analytics) of rollback and timeline.

Root cause analysis (RCA) initiated within 4 hours of rollback.

Fix implemented and validated on staging environment.

Re-cutover scheduled after fix validated — re-enters validation pipeline from L2.

Post-mortem documented within 5 business days.

## 5.3 Rollback Scope

Rollback is scoped to the affected wave — not the entire site:

| Scenario | Rollback Scope | Impact on Other Waves |
| --- | --- | --- |
| Wave 3 (country EN) fails validation | Only Wave 3 paths revert to AEM | Wave 1 (global) and Wave 2 (regional) remain on EDS — unaffected |
| Single locale in Wave 4 has issues | Only that locale reverts | All other translated locales remain on EDS |
| Commerce pods not rendering | Pod URLs revert to AEM servlet | All page content remains on EDS — only pods affected |
| Global infrastructure issue | All waves revert to AEM | Full rollback — rare scenario; requires CDN-level change |

# 6. Content Freeze & Governance

## 6.1 Content Freeze Windows

| Phase | Duration | Scope | What Authors Cannot Do | What Authors Can Do |
| --- | --- | --- | --- | --- |
| Pre-migration freeze | 5 business days before wave start | Pages in active wave scope | Edit, publish, delete, or move pages in scope | Edit pages NOT in current wave scope |
| Migration execution | 2-5 days (depends on page count) | Pages being actively migrated | Any changes to pages in scope | Author on DA for already-migrated pages |
| Validation window | 3-5 days post-migration | All pages in wave | Publish changes that could affect validation | Review content on EDS preview; flag issues |
| Post-cutover soak | 72 hours after traffic switch | All pages in wave | Major structural changes | Minor content fixes on DA (typos, images) |

## 6.2 Communication Plan

| Timing | Communication | Audience | Channel |
| --- | --- | --- | --- |
| T-10 days | Wave announcement — scope, dates, freeze schedule | All content authors in wave scope | Email + Teams channel |
| T-5 days | Content freeze begins — reminder with page list | Authors + regional leads | Email + Teams alert |
| T-0 (migration start) | Migration in progress — status updates every 4 hours | All stakeholders | Teams channel + status page |
| Migration complete | Validation phase started — preview URLs shared for review | Authors + QA + SEO | Email with links |
| Validation sign-off | Traffic switch scheduled — date/time confirmed | All stakeholders + commerce | Email + calendar invite |
| Cutover complete | Wave live on EDS — 72hr soak begins — monitoring active | All stakeholders | Email + Teams announcement |
| Soak complete | Wave confirmed stable — content editing open on DA | Authors + regional leads | Email + DA training reminder |

# 7. Validation Checklists

## 7.1 Pre-Cutover Checklist (Go/No-Go)

All items must be GREEN before traffic switch approval:

| # | Check | Status | Owner |
| --- | --- | --- | --- |
| 1 | All pages in wave scope created in DA (page count matches approved list) | ☐ | Migration lead |
| 2 | L1 automated validation passing for 100% of pages | ☐ | Dev team |
| 3 | L2 SEO validation complete — no P1 SEO issues | ☐ | SEO team |
| 4 | L2 Performance validation — Lighthouse ≥ 95 on all template samples | ☐ | Dev team |
| 5 | L3 Visual QA complete — no P1/P2 visual defects open | ☐ | QA team |
| 6 | L3 Form testing complete — all forms submit successfully | ☐ | QA + backend team |
| 7 | Redirect spreadsheet uploaded and all redirects verified (301, correct destination) | ☐ | SEO + dev team |
| 8 | Rollback procedure documented and tested (dry run on staging) | ☐ | DevOps |
| 9 | Content freeze confirmed — no edits in scope during freeze window | ☐ | Content lead |
| 10 | Monitoring dashboards configured and alerting active | ☐ | DevOps |
| 11 | Commerce team sign-off (if Wave 5 / pods in scope) | ☐ | Commerce team |
| 12 | Stakeholder sign-off to proceed with traffic switch | ☐ | TFS program lead |

## 7.2 Post-Cutover Checklist (72-Hour Soak)

| # | Check | When | Owner |
| --- | --- | --- | --- |
| 1 | All redirects resolving correctly (spot-check 50 URLs) | Hour 1 | Dev team |
| 2 | No 5xx errors in CDN logs | Hour 1-4 | DevOps |
| 3 | Forms submitting successfully (test each form type once) | Hour 1-4 | QA team |
| 4 | Google Search Console — no new crawl errors | Day 1 | SEO team |
| 5 | Analytics tracking firing correctly (page views, events) | Day 1 | Analytics team |
| 6 | Organic traffic within expected range (±10% of baseline) | Day 2 | SEO team |
| 7 | Core Web Vitals stable (RUM data) | Day 2-3 | Dev team |
| 8 | No P1/P2 bugs reported by content authors | Day 1-3 | QA team |
| 9 | Commerce pod rendering confirmed (if applicable) | Day 1 | Commerce team |
| 10 | Formal wave sign-off — wave declared stable | Day 3+ | Program lead |

# 8. Timeline & Milestones

┌────────────────────────────────────────────────────────────────────────────────┐
│                     MIGRATION TIMELINE (HIGH LEVEL)                             │
├────────────────────────────────────────────────────────────────────────────────┤
│                                                                                │
│  Week 1-3          Week 4-7          Week 8-11         Week 12-15              │
│  ┌──────┐          ┌──────┐          ┌──────┐          ┌──────┐               │
│  │Wave 0│          │Wave 1│          │Wave 2│          │Wave 3│               │
│  │Infra │──────────│Global│──────────│Region│──────────│Cntry │               │
│  │Setup │          │  EN  │          │  EN  │          │  EN  │               │
│  └──────┘          └──────┘          └──────┘          └──────┘               │
│                                                                                │
│                     Week 16-22        Week 23-25                               │
│                     ┌──────┐          ┌──────┐                                 │
│                     │Wave 4│          │Wave 5│                                 │
│                     │Trans-│──────────│Pods/ │                                 │
│                     │lated │          │Commrc│                                 │
│                     └──────┘          └──────┘                                 │
│                                                                                │
│  Key Milestones:                                                               │
│  • Week 3:  Infrastructure validated, MSM structure live                       │
│  • Week 7:  Global/en live on EDS (first production traffic)                   │
│  • Week 11: Regional EN hubs live                                              │
│  • Week 15: Country EN sites live                                              │
│  • Week 22: All translated locales live                                        │
│  • Week 25: Commerce pods cutover complete                                     │
│  • Week 26: AEM 6.4 decommissioning eligible (after final soak)               │
│                                                                                │
└────────────────────────────────────────────────────────────────────────────────┘

Important: Timeline is indicative and subject to TFS content team availability, delta page list approvals, and commerce team readiness for pod cutover. Durations may compress or expand based on page volumes per wave.

# 9. Risks & Mitigations

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Content changes made during freeze violate migration integrity | Medium | High | Strict freeze enforcement; content lock on AEM pages in scope; daily freeze compliance checks |
| R2 | Delta page identification misses pages with component-level overrides | Medium | Medium | Script uses cq:isCancelled detection at component level; TFS reviews full delta list before approval |
| R3 | Redirect spreadsheet incomplete — causes 404s post-cutover | High | High | Pre-cutover redirect validation (100% tested); 404 monitoring within first hour; rapid redirect addition process |
| R4 | Form submission backend not ready for EDS-originated requests | Low | High | Early backend testing (Wave 1); form pilot before bulk migration; Eloqua/endpoint validation |
| R5 | MSM inheritance serves wrong content (EN content to translated locale) | Medium | High | Translated locales migrate ALL pages (no inheritance); validate sample pages per locale before cutover |
| R6 | Commerce team not ready for pod cutover timing | Medium | Medium | Pod cutover in separate wave (Wave 5); pilot single SKU first; commerce team owns their switch timing |
| R7 | Rollback takes longer than expected due to CDN cache | Low | Medium | Pre-test rollback procedure; CDN cache purge automation; documented TTL expectations |
| R8 | Author training incomplete — authors unable to edit on DA post-cutover | Medium | Medium | Training schedule aligned to wave dates; sample pages and authoring guides per block available before cutover |

# 10. RACI Matrix

| Activity | Adobe Dev | Adobe PM | TFS Content | TFS Dev/IT | TFS PM | Commerce |
| --- | --- | --- | --- | --- | --- | --- |
| Migration script development | R | A | I | C | I | — |
| Delta page list approval | C | I | R/A | C | I | — |
| Content freeze enforcement | I | C | R | C | A | — |
| Migration execution | R | A | I | C | I | — |
| L1 automated validation | R | A | I | I | I | — |
| L2 SEO validation | R | C | C | I | A | — |
| L3 Visual/Functional QA | C | I | R | C | A | — |
| Go/No-Go decision | C | R | C | C | A | C |
| Traffic switch (DNS/CDN) | R | A | I | C | I | — |
| 72-hour monitoring | R | A | C | C | I | C |
| Rollback decision | C | R | C | C | A | C |
| Pod cutover coordination | C | I | I | C | A | R |
| Author training | R | C | R | I | A | — |
| Post-cutover sign-off | C | C | R | C | A | C |

R = Responsible | A = Accountable | C = Consulted | I = Informed