Critical Change Management Steps

Change in Process for TFS Team
AEM 6.4 to Edge Delivery Services with Document Authoring

Prepared for: Thermo Fisher Scientific
Date: May 28, 2026
Status: Draft for Internal Review
Version: 1.0

# Table of Contents

1. Executive Summary

2. Content Authoring Process Changes

3. Governance & Controls

4. Intake & Request Management

5. Operational Model Changes

6. MSM & Inheritance Model Changes

7. Training & Enablement Plan

8. Risk Register & Mitigations

9. Recommended Pilot Approach

10. Implementation Sequencing

11. Summary: Critical Process Changes at a Glance

Appendix A: Glossary

Appendix B: Document References

# Document Purpose

This document identifies and details the critical change management steps required for the Thermo Fisher Scientific (TFS) web team as they transition from AEM 6.4 to Edge Delivery Services (EDS) with Document Authoring (DA). Each use case identifies the current-state process, future-state process, delta/impact, and recommended change management actions.

Audience: TFS Corporate Web Team, Regional Content Authors, Governance & Operations Leads, Adobe Solution Delivery Team

# 1. Executive Summary

The migration from AEM 6.4 to EDS with DA represents a fundamental shift in operating model across five key dimensions:

| Dimension | AEM 6.4 (Current) | EDS with DA (Future) |
| --- | --- | --- |
| Authoring Model | Component-based in AEM Author UI | Document-based in Google Docs/SharePoint |
| Content Storage | JCR Repository | Google Drive / SharePoint |
| Publishing Model | Replication agents + Dispatcher | Preview & Publish via aem.live |
| Governance | Template policies + component restrictions | Configuration sheets + folder governance |
| Inheritance | MSM with component-level LiveCopy | Page-level inheritance with planned enhancements |

## Critical Success Factors

Phased rollout with pilot validation before full-scale migration

Dedicated enablement program for ~200 content authors

Governance model redesign aligned to configuration-driven controls

Clear escalation and support model during transition

# 2. Content Authoring Process Changes

## 2.1 Page Creation

| Aspect | Current State (AEM 6.4) | Future State (EDS + DA) | Impact |
| --- | --- | --- | --- |
| Tool | AEM Author UI (Sites Console) | Google Docs or Microsoft SharePoint | HIGH |
| Method | Select template > Create page in content tree | Create document from template in shared drive folder | HIGH |
| Template Enforcement | AEM Template Policies restrict available components | Folder-level document templates; content structure defined by document format | MEDIUM |
| Preview | AEM Preview mode / Preview instance | Live preview via .page URL (near-instant) | LOW |
| Metadata | Page Properties dialog in AEM | Metadata block within document or sheet-based configuration | MEDIUM |

Change Management Actions:

Action 1 — Training Program: Develop role-based training curriculum for document-based authoring (estimated 4-8 hours per author cohort)

Action 2 — Template Library: Create pre-configured document templates mirroring existing AEM templates to minimize cognitive shift

Action 3 — Quick Reference Guides: Produce visual comparison guides showing "how you do it today vs. how you'll do it tomorrow"

Action 4 — Sandbox Environment: Provide practice environment for authors to experiment without production impact

Action 5 — Champion Network: Identify 10-15 power users across regions as early adopters and peer coaches

## 2.2 Component/Block Authoring

| Aspect | Current State (AEM 6.4) | Future State (EDS + DA) | Impact |
| --- | --- | --- | --- |
| Adding Content Blocks | Drag-and-drop components from sidekick/side panel | Insert content sections using defined patterns (tables, headings, separators) | HIGH |
| Block Configuration | Component dialogs with dropdowns, checkboxes, fields | Document structure conventions; block options via table formatting | HIGH |
| Rich Text Editing | AEM RTE with configured plugins | Native document editor formatting | MEDIUM |
| Image Management | DAM asset picker within AEM | Insert images directly in document; assets from drive or DAM | MEDIUM |
| Variant Selection | Component dialog dropdowns | Block name variations in document table headers | MEDIUM |

Change Management Actions:

Produce comprehensive block catalog with visual examples, authoring patterns, and naming conventions

Document every current AEM component and its corresponding DA block pattern

Define and socialize the "rules" for document-based block authoring

Implement content validation tools or "preflight" checks to catch authoring errors before publish

Prioritize high-frequency blocks for Day 1, introduce advanced blocks in subsequent phases

## 2.3 Multi-Language / Regional Content Creation

| Aspect | Current State (AEM 6.4) | Future State (EDS + DA) | Impact |
| --- | --- | --- | --- |
| Language Copy Creation | MSM LiveCopy rollout creates localized pages | Copy document to regional folder; modify as needed | HIGH |
| Component-Level Inheritance | Individual components inherit from blueprint; override selectively | Page-level copy; sections managed independently per locale | HIGH |
| Translation Integration | AEM Translation Framework with connector | Translation connector integration (API-based) | MEDIUM |
| Rollout Trigger | Author triggers rollout from blueprint to LiveCopies | Manual or automated sync via defined process (planned enhancement) | HIGH |

Change Management Actions:

Conduct workshops explaining the shift from component-level to page-level content management

Define new processes for how global changes propagate to regional content

Document standard operating procedures for keeping regional content aligned with global updates

Assess each region's current inheritance usage and quantify the operational delta

Identify opportunities for scripted/automated content synchronization to offset manual overhead

# 3. Governance & Controls

## 3.1 Template & Content Governance

| Aspect | Current State (AEM 6.4) | Future State (EDS + DA) | Impact |
| --- | --- | --- | --- |
| Template Enforcement | AEM Template policies; allowed components defined per template | Folder-level permissions; document templates as governance layer | HIGH |
| Component Restrictions | Policy-based component allowlisting per content area | Block validation via automated checks or editorial review | MEDIUM |
| Content Structure Rules | Paragraph systems with locked/unlocked areas | Document structure conventions enforced through training + validation | HIGH |
| Brand Compliance | Component designs enforce brand constraints | Style/CSS enforcement at delivery layer; author flexibility in document | MEDIUM |
| Access Control | AEM user groups + ACLs on content paths | Google Drive / SharePoint permissions on folders | MEDIUM |

Change Management Actions:

Redesign governance framework from "platform-enforced" to "process-enforced + automated validation"

Design folder hierarchy that maps to governance boundaries (region, brand, content type)

Create detailed permission matrix mapping current AEM groups to Drive/SharePoint access levels

Implement automated content validation (pre-publish checks) to replace AEM policy enforcement

Establish monitoring/reporting for content compliance, authoring adherence, and quality metrics

Define clear escalation paths for governance violations detected post-publish

## 3.2 Approval & Publishing Workflows

| Aspect | Current State (AEM 6.4) | Future State (EDS + DA) | Impact |
| --- | --- | --- | --- |
| Approval Process | Custom AEM workflow (43-step Major / 29-step Simple) | Configuration-based approval via Request Publish; multi-step enhancement planned | HIGH |
| Workflow Routing | Code-based routing with conditional logic | Path-based configuration in admin sheets | MEDIUM |
| Reviewer Experience | AEM Inbox with task assignment | Email/notification-based with approve/reject actions | MEDIUM |
| Publishing Trigger | Workflow completion activates replication | Approval triggers publish to .live environment | LOW |
| Scheduled Publishing | AEM Scheduler / workflow-based scheduled activation | Planned enhancement; manual publish timing in interim | HIGH |
| Bulk Operations | AEM bulk activation tools | Bulk publish via admin API or site-level operations | MEDIUM |

Change Management Actions:

Review current 43-step workflow to identify true business logic steps vs. infrastructure steps

Define transitional approval process for Day 1 (single-step) while multi-step enhancement is delivered

Train workflow administrators on sheet-based workflow configuration

Design and implement notification/communication flows for approval requests

Document interim manual scheduling process until platform-native scheduling is available

Step-by-step guide for migrating each workflow variant to the new model

Dependency Note: Multi-step sequential approval requires a planned DA product enhancement. Adobe engineering has confirmed commitment to deliver this capability through direct collaboration with TFS. Timeline and milestone commitments should be documented in the SOW.

## 3.3 Content Rollback & Version Control

| Aspect | Current State (AEM 6.4) | Future State (EDS + DA) | Impact |
| --- | --- | --- | --- |
| Version History | AEM Versioning (manual + workflow-triggered) | Document version history (Google Docs/SharePoint native) | LOW |
| Rollback | Restore specific version in AEM; re-activate | Revert document to prior version; re-publish | LOW |
| Audit Trail | AEM Audit Log | Document revision history + publish event logs | MEDIUM |
| Comparison | AEM version diff tool | Document comparison (native to Google Docs/SharePoint) | LOW |

Change Management Actions:

Document new versioning and rollback procedures using document platform capabilities

Validate that document revision history meets compliance/audit requirements

Include version management in author training curriculum

# 4. Intake & Request Management

## 4.1 Web Request Intake Process

| Aspect | Current State (AEM 6.4) | Future State (EDS + DA) | Impact |
| --- | --- | --- | --- |
| Request Types | New page, content update, component config, template change | New document, content update, block addition, style change | MEDIUM |
| Complexity Assessment | Based on component complexity + workflow requirements | Based on content structure + block patterns | LOW |
| Skill Requirements | AEM authoring proficiency required | Document editing proficiency (lower barrier to entry) | MEDIUM |
| Self-Service Scope | Limited by AEM access + training | Broader self-service potential via familiar document tools | MEDIUM |
| Developer Involvement | Template/component changes require developer | Block/style changes require developer; content changes do not | LOW |

Change Management Actions:

Update web request intake forms to reflect new request types and complexity tiers

Revise triage criteria based on new platform capabilities (more self-service = fewer centralized requests)

Identify content types/requests that can shift from centralized to self-service with DA

Review and adjust SLAs based on new publishing speed (near-instant publish vs. replication delays)

Model impact on team capacity as authoring becomes more distributed

## 4.2 Request Routing & Assignment

| Aspect | Current State (AEM 6.4) | Future State (EDS + DA) | Impact |
| --- | --- | --- | --- |
| Routing Logic | Ticket-based assignment + AEM workflow routing | Ticket-based assignment + folder/path-based approval routing | LOW |
| Skill Matching | Route to AEM-trained resources | Route based on content type; lower technical barrier | LOW |
| Handoff Process | Developer builds in AEM > Author reviews > Approve | Author creates in document > Reviewer approves > Publish | MEDIUM |

Change Management Actions:

Revise RACI matrix to reflect shifted responsibilities

Simplify handoff process where direct authoring replaces developer intermediation

Update team skill matrix and hiring/training profiles for DA-centric workflows

# 5. Operational Model Changes

## 5.1 Day-to-Day Content Operations

| Aspect | Current State (AEM 6.4) | Future State (EDS + DA) | Impact |
| --- | --- | --- | --- |
| Daily Author Workflow | Login to AEM Author > Navigate > Edit > Preview > Submit | Open shared document > Edit > Preview via URL > Request publish | HIGH |
| Collaboration | Limited concurrent editing; check-in/check-out | Real-time collaborative editing (native to Google Docs/SharePoint) | MEDIUM (Positive) |
| Content Discovery | AEM search + content tree navigation | Drive/SharePoint search + folder navigation | MEDIUM |
| Asset Management | AEM DAM integration with asset picker | Direct image insertion or DAM connector | MEDIUM |
| Performance Monitoring | Dispatcher cache + CDN monitoring | Edge delivery (built-in Lighthouse 100 optimization) | LOW |

Change Management Actions:

Create role-specific "day in the life" guides showing new daily workflows

Proactively communicate collaboration improvements (real-time co-editing, familiar tools)

Train authors on finding and organizing content in the new storage model

Establish tiered support model (self-service > peer champions > central team > Adobe support)

## 5.2 Environment & Deployment Operations

| Aspect | Current State (AEM 6.4) | Future State (EDS + DA) | Impact |
| --- | --- | --- | --- |
| Environments | Author > Preview > Publish (AEM instances) | Document (source) > Preview (.page) > Live (.live) | MEDIUM |
| Code Deployment | AEM packages via Cloud Manager | Git push > automatic code sync to edge | MEDIUM |
| Content Deployment | Replication (Tree/individual activation) | Publish action (instant edge delivery) | LOW (Improvement) |
| Environment Parity | Often drift between Author and Publish | Preview and Live architecturally identical | LOW (Improvement) |
| Hotfix Process | Emergency package deployment; dispatcher flush | Git commit to main (instant propagation) | LOW (Improvement) |

Change Management Actions:

Document environment equivalencies for operations team

Train DevOps/operations on Git-based deployment model

Update incident response procedures for new deployment and rollback model

## 5.3 Monitoring, Analytics & Reporting

| Aspect | Current State (AEM 6.4) | Future State (EDS + DA) | Impact |
| --- | --- | --- | --- |
| Site Performance | Custom monitoring + CDN analytics | Real User Monitoring (RUM) built into EDS | LOW (Improvement) |
| Content Analytics | AEM + Adobe Analytics integration | Adobe Analytics / Launch integration maintained | LOW |
| Author Activity Reporting | AEM Audit logs + custom reports | Document activity logs + publish event tracking | MEDIUM |
| Uptime Monitoring | Infrastructure monitoring (AEM instances) | Edge network monitoring (Adobe-managed) | LOW (Improvement) |

Change Management Actions:

Identify current reports dependent on AEM data and establish equivalents

Train operations team on EDS Real User Monitoring capabilities

Build new operational dashboards aligned to EDS metrics and KPIs

# 6. MSM & Inheritance Model Changes

CRITICAL IMPACT AREA

## 6.1 Global-to-Local Content Propagation

| Aspect | Current State (AEM 6.4) | Future State (EDS + DA) | Impact |
| --- | --- | --- | --- |
| Inheritance Unit | Component-level (individual components inherit independently) | Page-level (entire document inherits; section-level enhancement planned) | CRITICAL |
| Override Behavior | Cancel inheritance on specific component; rest continues to inherit | Copy page to locale folder; manage independently or re-sync manually | CRITICAL |
| Rollout Mechanism | MSM rollout configs (on modification, on activation, manual) | Manual copy/sync or automated scripting (planned enhancement) | HIGH |
| Cascade Behavior | Multi-level cascade (Global > Region > Country > Language) | Folder hierarchy with copy/reference model | HIGH |
| Conflict Resolution | AEM conflict resolution dialogs on rollout | Manual comparison and merge; tooling under development | HIGH |

Change Management Actions:

CRITICAL — Conduct detailed workshops per region to map current inheritance dependencies and quantify impact

Classify all pages by inheritance complexity: Simple (full page), Moderate (1-3 overrides), Complex (heavy overrides)

Co-design with regional teams the new model for managing global-to-local content propagation

Invest in scripted synchronization tooling to offset loss of automatic component-level inheritance

MANDATORY — Run inheritance pilot on representative page set before committing to full migration

Model the additional authoring effort required under page-level inheritance vs. component-level

Critical Risk: This is the single highest-impact change for TFS operations. Without adequate tooling, automation, and process redesign, the shift from component-level to page-level inheritance could materially increase operational burden for ~200 content authors managing multi-region content.

## 6.2 Regional Content Independence

| Aspect | Current State (AEM 6.4) | Future State (EDS + DA) | Impact |
| --- | --- | --- | --- |
| Non-MSM Countries | Independent content trees (no inheritance) | Independent folder structures (minimal change) | LOW |
| Hybrid Models | Mix of inherited and independent pages | Folder-based organization with clear separation | LOW |
| Regional Autonomy | Controlled by MSM configuration + permissions | Controlled by folder permissions + governance process | MEDIUM |

Change Management Actions:

Document which regions are independent vs. inherited; plan accordingly

Design folder structures that balance regional autonomy with corporate oversight

# 7. Training & Enablement Plan

## Recommended Training Phases

| Phase | Audience | Content | Duration | Timing |
| --- | --- | --- | --- | --- |
| Phase 0: Awareness | All 200+ authors | What's changing, why, timeline, benefits | 1 hour (webinar) | 8 weeks before Go-Live |
| Phase 1: Foundation | Pilot group (15-20) | Hands-on document authoring, blocks, preview, publish | 2 days | 6 weeks before Go-Live |
| Phase 2: Validation | Pilot group | Real content migration exercises, feedback capture | 2 weeks (ongoing) | 4-6 weeks before Go-Live |
| Phase 3: Core Training | All authors (cohorts of 20-25) | Role-specific training, hands-on exercises, Q&A | 1.5 days per cohort | 2-4 weeks before Go-Live |
| Phase 4: Advanced | Power users, workflow admins, regional leads | Governance config, advanced blocks, troubleshooting | 1 day | 1-2 weeks before Go-Live |
| Phase 5: Hypercare | All authors | Office hours, 1:1 support, FAQ updates | 4 weeks | Go-Live + 4 weeks |

## Training Artifacts Required

Video library (short-form, task-specific)

Visual quick-reference cards (printable/digital)

Interactive sandbox environment

Block catalog with authoring examples

FAQ document (living, updated during hypercare)

Governance and process reference guide

"AEM 6.4 to DA" translation cheat sheet

# 8. Risk Register & Mitigations

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Component-level inheritance loss increases operational burden beyond capacity | High | Critical | Invest in automation; capacity modeling; mandatory pilot |
| R2 | Multi-step approval enhancement not delivered on timeline | Medium | High | Define interim process; SOW milestone with Adobe commitment |
| R3 | Scheduled publishing gap causes missed launch windows | Medium | High | Manual workaround documented; confirm Adobe roadmap |
| R4 | Author adoption resistance due to unfamiliar tools | Medium | Medium | Early engagement, champions, demonstrate benefits, extended hypercare |
| R5 | Governance gaps during transition | Medium | High | Automated validation tooling; clear escalation paths |
| R6 | Regional teams unprepared for changed propagation model | High | High | Region-specific assessments; dedicated workshops; phased rollout |
| R7 | Self-service expansion creates content quality issues | Low | Medium | Automated quality checks; editorial review layer |
| R8 | Platform immaturity introduces unexpected limitations | Medium | High | Pilot-first approach; feature dependency tracker; contractual commitments |

# 9. Recommended Pilot Approach

Before full-scale migration, TFS should execute a structured pilot to validate process changes.

## Pilot Scope

Page Set: 20-30 representative pages spanning simple, moderate, and complex inheritance patterns

Regions: 2-3 regions with different inheritance models

Authors: 15-20 authors across roles (global, regional, local)

Duration: 4-6 weeks

## Pilot Validation Criteria

| Category | Validation Question | Success Criteria |
| --- | --- | --- |
| Authoring | Can authors create/edit content with acceptable efficiency? | Task completion within 120% of current AEM time after training |
| Inheritance | Can global-to-local propagation be managed operationally? | Regional sync achievable within defined SLA |
| Governance | Are governance controls adequate without AEM policies? | Zero unauthorized content published during pilot |
| Workflows | Does approval process meet business requirements? | All required approvals captured before publish |
| Performance | Does publishing meet speed requirements? | Content live within X minutes of approval |
| Scale | Can the model support daily request volume? | Process handles simulated peak load without degradation |

Pilot Decision Gate: At pilot completion, TFS leadership will have data to make an informed go/no-go decision for full migration based on empirical evidence rather than assumptions.

# 10. Implementation Sequencing Recommendation

Phase 0: Foundation & Planning (Weeks 1-4)

Governance model redesign

Folder structure & permissions design

Training curriculum development

Automation tooling requirements

Phase 1: Pilot (Weeks 5-10)

Migrate representative page set

Author enablement (pilot cohort)

Validate inheritance model

Validate governance controls

Capture metrics & feedback

Phase 2: Decision Gate (Week 11)

Pilot results review

Capacity impact assessment

Go/No-Go decision

SOW/scope adjustments if needed

Phase 3: Scaled Migration (Weeks 12-24+)

Region-by-region rollout

Author training (all cohorts)

Content migration execution

Governance activation

Hypercare support

Phase 4: Optimization (Ongoing)

Process refinement based on operational data

Automation enhancements

Advanced capability adoption

Platform enhancement uptake

# 11. Summary: Critical Process Changes at a Glance

| # | Process Area | Change Severity | Key Action Required |
| --- | --- | --- | --- |
| 1 | Content Authoring Tool | HIGH | Train 200+ authors on document-based authoring |
| 2 | Block/Component Authoring | HIGH | Document all block patterns; create authoring guides |
| 3 | Inheritance Model | CRITICAL | Redesign operating model; pilot mandatory; automation investment |
| 4 | Approval Workflows | HIGH | Design interim process; confirm multi-step enhancement timeline |
| 5 | Governance Enforcement | HIGH | Shift from platform-enforced to process + automation-enforced |
| 6 | Regional Content Management | HIGH | Region-specific impact assessment; new propagation SOPs |
| 7 | Intake & Request Management | MEDIUM | Update intake forms, triage criteria, SLAs |
| 8 | Scheduled Publishing | HIGH | Interim manual process; roadmap dependency |
| 9 | Environment Operations | MEDIUM | Retrain operations on Git-based deployment |
| 10 | Reporting & Monitoring | MEDIUM | Transition dashboards to EDS/RUM metrics |

# Appendix A: Glossary

| Term | Definition |
| --- | --- |
| DA (Document Authoring) | Adobe's document-based authoring model where content is created in Google Docs or Microsoft SharePoint |
| EDS (Edge Delivery Services) | Adobe's edge-optimized delivery platform providing near-instant page loads |
| MSM (Multi-Site Manager) | AEM feature enabling content inheritance and rollout across site hierarchies |
| LiveCopy | An AEM page that inherits content from a blueprint/source page via MSM |
| Universal Editor | Adobe's next-generation visual editor supporting in-context editing |
| RUM (Real User Monitoring) | Built-in EDS performance monitoring based on actual user page load data |
| JCR (Java Content Repository) | The content storage layer in traditional AEM (6.x and Cloud) |
| xWalk | AEM Cloud with Universal Editor using JCR as the content backend |

# Appendix B: Document References

Approval & Publishing Workflows Comparison (companion document)

AEM Edge Delivery Services Documentation — www.aem.live/docs/

Universal Editor Documentation — Adobe Experience League

TFS Solution Design Document (SDD)